## Sprint Overview
Agile Sprint Plan — Patient Feedback IVR
Conversational IVR Modernization Framework G1 ¦ Rhitam Mondal ¦ Infosys AI Internship 2026
Project | AI-Enabled Conversational Patient Feedback IVR (Web Simulator Approach)
Team Member | Rhitam Mondal — B.Tech CSBS, Meghnad Saha Institute of Technology
Internship | Infosys Virtual Internship — AI Domain — Group 1
Duration | 4 Sprints (Milestones 1–4) ¦ April – May 2026
Methodology | Agile Scrum — 1 Sprint per Milestone ¦ Sprint length: 1 week
Sprint | Milestone | Goal | Start | End | Story Points | Completed | Velocity % | Status | Key Output
S1 | Milestone 1 | Legacy IVR analysis, requirements, documentation | 01 Apr 2026 | 07 Apr 2026 | 20 | 20 |  | Complete | M1 PDF Document
S2 | Milestone 2 | Build Flask backend, menu engine, web simulator UI | 08 Apr 2026 | 14 Apr 2026 | 34 | 34 |  | Complete | main.py, menu_engine.py, index.html
S3 | Milestone 3 | AI NLU engine, 14-state FSM, REST API upgrade | 15 Apr 2026 | 28 Apr 2026 | 55 | 55 |  | Complete | conversation_engine.py, ivr_flow_controller.py
S4 | Milestone 4 | 100 automated tests, Docker, GitHub Actions CI/CD | 29 Apr 2026 | 07 May 2026 | 42 | 42 |  | Complete | test suite, Dockerfile, ci-cd.yml
| TOTAL | [7 empty] | All milestones delivered

## Sprint 1 — M1 Analysis
Sprint 1 — Milestone 1
Analyse legacy IVR system, define requirements and project scope
Sprint | Sprint 1 (Milestone 1)
Dates | 01 Apr 2026 – 07 Apr 2026
Goal | Analyse legacy IVR system, define requirements and project scope
# | User Story / Task | Category | Priority | Est. Points | Act. Points | Status | Owner | Notes
1 | Study existing hospital IVR DTMF system and identify pain points | Research | High | 3 | 3 | Done | Rhitam | Documented in M1 PDF
2 | Define project scope — Patient Feedback IVR with web simulator approach | Planning | High | 2 | 2 | Done | Rhitam | Web simulator chosen over telephony
3 | Identify system components: ACS, BAP, middleware, IVR engine | Architecture | High | 3 | 3 | Done | Rhitam | Architecture diagram drawn
4 | Define patient feedback categories: Doctor, Nurse, Facility, Wait time | Requirements | High | 2 | 2 | Done | Rhitam | 5 rating dimensions defined
5 | Document functional requirements for conversational IVR | Requirements | High | 3 | 3 | Done | Rhitam | Included in M1 document
6 | Document non-functional requirements (performance, security) | Requirements | Medium | 2 | 2 | Done | Rhitam | Response time < 500ms target set
7 | Prepare Milestone 1 PDF document for submission | Documentation | High | 5 | 5 | Done | Rhitam | FINALE MILESTONE 1 DOCUMENT.pdf
TOTAL

## Sprint 2 — M2 Integration
Sprint 2 — Milestone 2
Build Flask backend, IVR menu engine, session manager, and web simulator UI
Sprint | Sprint 2 (Milestone 2)
Dates | 08 Apr 2026 – 14 Apr 2026
Goal | Build Flask backend, IVR menu engine, session manager, and web simulator UI
# | User Story / Task | Category | Priority | Est. Points | Act. Points | Status | Owner | Notes
1 | Set up Flask project structure and install dependencies | Setup | High | 2 | 2 | Done | Rhitam | Flask installed, requirements.txt created
2 | Build main.py — Flask application entry point and routing | Backend | High | 4 | 4 | Done | Rhitam | GET / and POST /start, /input endpoints
3 | Build menu_engine.py — Define all IVR menus and navigation options | Backend | High | 5 | 5 | Done | Rhitam | Main, consultation, nursing, facilities menus
4 | Build session_manager.py — Session creation, update, and termination | Backend | High | 4 | 4 | Done | Rhitam | UUID-based sessions with in-memory store
5 | Build database.py — Feedback persistence to JSON file | Backend | High | 3 | 3 | Done | Rhitam | feedback_records.json storage
6 | Build index.html — Browser-based IVR simulator UI | Frontend | High | 6 | 6 | Done | Rhitam | Fetch API, menu rendering, response display
7 | Manual end-to-end testing of complete feedback flow | Testing | High | 4 | 4 | Done | Rhitam | All 6 manual test scenarios passed
8 | Push all files to GitHub repository | DevOps | Medium | 2 | 2 | Done | Rhitam | Committed to main branch
9 | Prepare Milestone 2 document | Documentation | Medium | 4 | 4 | Done | Rhitam | MILESTONE_2_DOCUMENT_RHITAM.pdf
TOTAL

## Sprint 3 — M3 AI Interface
Sprint 3 — Milestone 3
Build AI conversation engine, 14-state FSM, and production REST API
Sprint | Sprint 3 (Milestone 3)
Dates | 15 Apr 2026 – 28 Apr 2026
Goal | Build AI conversation engine, 14-state FSM, and production REST API
# | User Story / Task | Category | Priority | Est. Points | Act. Points | Status | Owner | Notes
1 | Design 14-state FSM dialogue flow diagram | Architecture | High | 3 | 3 | Done | Rhitam | States: WELCOME → THANK YOU + ERROR/EXIT
2 | Build IVRState enum and IVRSession dataclass | Backend | High | 3 | 3 | Done | Rhitam | 14 states, full session data model
3 | Build IVRFlowController — state machine with all handlers | Backend | High | 8 | 8 | Done | Rhitam | 14 handler methods, transition validation
4 | Build AIConversationEngine — rule-based NLU pipeline | AI | High | 7 | 7 | Done | Rhitam | 8 intent classes, rating extractor, ID regex
5 | Add empathetic response wrapping based on rating sentiment | AI | Medium | 2 | 2 | Done | Rhitam | Low/mid/high rating prefix messages
6 | Add LLM fallback hook (use_llm=True mode) | AI | Low | 3 | 3 | Done | Rhitam | Claude/OpenAI compatible interface
7 | Build FeedbackStore — patient DB lookup and persistence | Backend | High | 4 | 4 | Done | Rhitam | Mock EHR, JSON storage, stats API
8 | Build simulator_app.py — 5 REST endpoints + embedded browser UI | Backend | High | 8 | 8 | Done | Rhitam | POST start, POST input, GET summary, GET all, GET health
9 | Upgrade browser UI — chat window, quick-reply buttons, state bar | Frontend | High | 5 | 5 | Done | Rhitam | Auto-updating quick replies per IVR state
10 | Structure code as Python package (src/ with __init__.py) | DevOps | Medium | 2 | 2 | Done | Rhitam | src/ivr_engine, ai_engine, web_simulator, middleware
11 | Write 31 unit tests for M3 (test_ivr_system.py) | Testing | High | 5 | 5 | Done | Rhitam | All 31 tests passing
12 | Prepare Milestone 3 document | Documentation | Medium | 5 | 5 | Done | Rhitam | MILESTONE_3_DOCUMENT_RHITAM.pdf
TOTAL

## Sprint 4 — M4 Deployment
Sprint 4 — Milestone 4
Write 100 automated tests, containerize with Docker, set up GitHub Actions CI/CD
Sprint | Sprint 4 (Milestone 4)
Dates | 29 Apr 2026 – 07 May 2026
Goal | Write 100 automated tests, containerize with Docker, set up GitHub Actions CI/CD
# | User Story / Task | Category | Priority | Est. Points | Act. Points | Status | Owner | Notes
1 | Write extended AI engine tests — 22 NLU edge cases | Testing | High | 4 | 4 | Done | Rhitam | Natural language variants, empty input, long comments
2 | Write extended IVR flow tests — 9 FSM state machine tests | Testing | High | 3 | 3 | Done | Rhitam | Retry logic, max retries → EXIT, history logging
3 | Write extended feedback store tests — 9 persistence tests | Testing | High | 3 | 3 | Done | Rhitam | Stats accuracy, recommend rate, cross-instance persistence
4 | Write Flask API integration tests — 11 endpoint tests | Testing | High | 4 | 4 | Done | Rhitam | All 5 endpoints, 400/404 errors, full dialogue via HTTP
5 | Write performance tests — 7 benchmark tests | Testing | Medium | 3 | 3 | Done | Rhitam | NLU 100 inputs < 1s, concurrent sessions, Flask response time
6 | Write E2E user flow tests — 9 full journey simulations | Testing | High | 4 | 4 | Done | Rhitam | Happy path, no-recommend, review-resubmit, 5 simultaneous
7 | Verify all 100 tests pass with 0 failures | Testing | High | 2 | 2 | Done | Rhitam | python -m pytest tests/ -v → 100 passed
8 | Write Dockerfile — production container with gunicorn | DevOps | High | 4 | 4 | Done | Rhitam | python:3.11-slim, 4 workers, non-root user, HEALTHCHECK
9 | Write docker-compose.yml — orchestrated deployment | DevOps | High | 3 | 3 | Done | Rhitam | Persistent volume, restart policy, health check
10 | Write GitHub Actions CI/CD pipeline (ci-cd.yml) | DevOps | High | 4 | 4 | Done | Rhitam | 3 stages: Test → Docker build + smoke test → Summary
11 | Write post_deployment_check.py validation script | DevOps | Medium | 2 | 2 | Done | Rhitam | 6 endpoint checks + response time validation
12 | Update requirements.txt with gunicorn, pytest, pytest-cov | DevOps | Medium | 1 | 1 | Done | Rhitam | Production + testing dependencies separated
13 | Prepare Milestone 4 document and Agile Sprint Plan | Documentation | High | 5 | 5 | Done | Rhitam | PDF + Excel documents for all milestones
TOTAL

## Burndown & Velocity
Burndown & Velocity Report
Sprint-by-Sprint Story Points ¦ Patient Feedback IVR Project
Sprint | Ideal Remaining | Actual Remaining | Completed Points | Sprint Points | Velocity %
Sprint 0 (Start) | 151 | 151 | 0 | 0
Sprint 1 — M1 Analysis | 113 | 131 | 20 | 20
Sprint 2 — M2 Integration | 75 | 97 | 34 | 34
Sprint 3 — M3 AI Interface | 25 | 42 | 55 | 55
Sprint 4 — M4 Deployment | 0 | 0 | 42 | 42
PROJECT TOTAL